## Dashboard
CEG Italia — Project Management Dashboard
Last updated: May 07, 2026 ¦ Owner: Lapo Lazzati ¦ Counterpart: Stephen Tanico (CEG)
Active Workstreams | 9 | Open Action Items | 29 | Due This Week | 1 | Overdue | 0
ID | Workstream | Priority | Owner | Status | Deadline | Start | End
WS1 | Commercial Terms (Retainer + 7% Fee) | P1 | Steve + Lapo | In Progress | 2026-05-22 | 2026-05-04 | 2026-05-22
WS2 | Voluntary Cleanup - Industrial Pipeline | P2 | Lapo | In Progress | Ongoing | 2026-05-04 | 2026-07-31
WS3 | Cementificio Luca - First Live Prospect | P2 | Lapo | Not Started | 2026-05-14 | 2026-05-04 | 2026-05-15
WS4 | Brenelli - Voluntary Referral Pipeline | P2 | Lapo | Not Started | 2026-05-21 | 2026-05-04 | 2026-05-22
WS5 | Mandated Cleanup - ARPA Approval Pathway | P3 | Steve + Lapo | Not Started | 2026-06-04 | 2026-05-11 | 2026-07-03
WS6 | Entity Setup + Liability Insurance | P3 | Lapo | Not Started | 2026-06-07 | 2026-05-11 | 2026-06-19
WS7 | Satellite Intelligence Partnership | P4 | Lapo | Not Started | 2026-06-30 | 2026-05-18 | 2026-07-03
WS8 | RDC Local Manufacturing | P4 | Lapo + CEG | Initial Contact Made | 2026-08-15 | 2026-05-25 | 2026-08-14
WS9 | Turkey / Istanbul Expansion | P5 | Lapo | On Hold | 2026-09-30 | 2026-06-01 | 2026-08-28
Status legend |  |  | Priority legend
Done | Completed |  | P1 | Critical / blocking
In Progress | Active work |  | P2 | High - active sales
Not Started | Queued |  | P3 | Medium - infra
On Hold | Paused / dependency |  | P4 | Normal - partnerships
Blocked | Blocked / overdue |  | P5 | Future / dependent

## Gantt
CEG Italia — Gantt Chart
Timeline: May 04, 2026 — Sep 18, 2026 · Each column = 1 week
◀ TODAY
[7 empty] | May 2026 |  |  |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026
ID | Workstream | Priority | Owner | Status | Start | End | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14
WS1 | Commercial Terms (Retainer + 7% Fee) | P1 | Steve + Lapo | In Progress | 2026-05-04 | 2026-05-22 | P1
WS2 | Voluntary Cleanup - Industrial Pipeline | P2 | Lapo | In Progress | 2026-05-04 | 2026-07-31 | P2
WS3 | Cementificio Luca - First Live Prospect | P2 | Lapo | Not Started | 2026-05-04 | 2026-05-15 | P2
WS4 | Brenelli - Voluntary Referral Pipeline | P2 | Lapo | Not Started | 2026-05-04 | 2026-05-22 | P2
WS5 | Mandated Cleanup - ARPA Approval Pathway | P3 | Steve + Lapo | Not Started | 2026-05-11 | 2026-07-03 |  | P3
WS6 | Entity Setup + Liability Insurance | P3 | Lapo | Not Started | 2026-05-11 | 2026-06-19 |  | P3
WS7 | Satellite Intelligence Partnership | P4 | Lapo | Not Started | 2026-05-18 | 2026-07-03 |  |  | P4
WS8 | RDC Local Manufacturing | P4 | Lapo + CEG | Initial Contact Made | 2026-05-25 | 2026-08-14 |  |  |  | P4
WS9 | Turkey / Istanbul Expansion | P5 | Lapo | On Hold | 2026-06-01 | 2026-08-28 |  |  |  |  | P5

## Workstreams
Workstream Definitions
ID | Workstream | Priority | Owner | Status | Deadline | Start | End | Notes / Strategic Context
WS1 | Commercial Terms (Retainer + 7% Fee) | P1 | Steve + Lapo | In Progress | 2026-05-22 | 2026-05-04 | 2026-05-22 | BLOCKING: must close before any client-facing move. Term sheet covers retainer, fee basis, exclusivity scope (Italy vs Mediterranean), expense policy.
WS2 | Voluntary Cleanup - Industrial Pipeline | P2 | Lapo | In Progress | Ongoing | 2026-05-04 | 2026-07-31 | Entry segment. Lawyer-led intros (Brenelli) + commercialisti channel. Focus: cement, chemical, fuel stations.
WS3 | Cementificio Luca - First Live Prospect | P2 | Lapo | Not Started | 2026-05-14 | 2026-05-04 | 2026-05-15 | Confirm company name, contaminant type, site size. Could be first paid feasibility.
WS4 | Brenelli - Voluntary Referral Pipeline | P2 | Lapo | Not Started | 2026-05-21 | 2026-05-04 | 2026-05-22 | Scope intent + collaboration structure with criminal env lawyer. Highest-leverage channel.
WS5 | Mandated Cleanup - ARPA Approval Pathway | P3 | Steve + Lapo | Not Started | 2026-06-04 | 2026-05-11 | 2026-07-03 | Decide path: senior geologist vs. Luca institutional contact. Map CEG US regulatory dossier for ARPA adaptation. Don't pitch this segment until path is clear.
WS6 | Entity Setup + Liability Insurance | P3 | Lapo | Not Started | 2026-06-07 | 2026-05-11 | 2026-06-19 | S.r.l. entity, RC professionale quote, commercialista consult, ~€100K capital plan. Required before Istanbul.
WS7 | Satellite Intelligence Partnership | P4 | Lapo | Not Started | 2026-06-30 | 2026-05-18 | 2026-07-03 | Scoping call → coverage, commercial model. Before/after CEG project validation. Brenelli on legal framing.
WS8 | RDC Local Manufacturing | P4 | Lapo + CEG | Initial Contact Made | 2026-08-15 | 2026-05-25 | 2026-08-14 | BioBlend + ISCO formulation specs, IP/licensing constraints, quality requirements.
WS9 | Turkey / Istanbul Expansion | P5 | Lapo | On Hold | 2026-09-30 | 2026-06-01 | 2026-08-28 | DEPENDS ON WS1 + WS6. Don't initiate before terms + entity. Frame as regional partner, not CEG-branded.

## Action Items
Action Items — Granular Tasks
WS | Task | Owner | Due Date | Status | Days to Due | Notes
WS1 | Draft term sheet covering retainer (€4K/mo) + 7% introducer fee + Italy exclusivity + expense policy | Lapo | 2026-05-15 | Not Started | 8 | Define fee basis: CEG contract value vs Lapo-introduced portion only
WS1 | Steve review + sign side letter | Steve | 2026-05-22 | Not Started | 15 | Blocking gate for all downstream activity
WS2 | Build target list: cement + chemical + fuel station polluters (channel partner shortlist) | Lapo | 2026-05-31 | In Progress | 24 | Reference Channel Partners shortlist sheet
WS2 | Define CEG voluntary-client offering (bench test entry, scoping call, prelim estimate) | CEG | 2026-06-15 | Not Started | 39 | Need pricing tiers and SLA for first contact
WS2 | Set up commercialisti channel funnel (Di Salvo, Rizzi) | Lapo | 2026-06-30 | Not Started | 54 | Tax DD as early warning system for contaminated sites
WS3 | Get full company name + contaminant type + approx site size from Luca | Lapo | 2026-05-14 | Not Started | 7 | Priority 3 in original doc
WS3 | Send 1-pager + CEG capability dossier to Luca | Lapo | 2026-05-21 | Not Started | 14 | Adapt from CEG US materials
WS3 | Schedule technical scoping call (CEG + Luca + Lapo) | Lapo | 2026-05-28 | Not Started | 21 | Confirm bench test feasibility
WS4 | Initial scoping call with Brenelli | Lapo | 2026-05-21 | Not Started | 14 | Volume of voluntary remediation inquiries, willingness to refer
WS4 | Propose referral / collaboration structure to Brenelli | Lapo | 2026-06-04 | Not Started | 28 | Fee share or co-branded approach
WS5 | Identify senior geologist with active ARPA relationships | Lapo | 2026-05-21 | Not Started | 14 | Alternative path to Luca's institutional contact
WS5 | Decision: geologist path vs. Luca institutional contact | Steve + Lapo | 2026-05-21 | Not Started | 14 | Priority 4 in original doc
WS5 | Map CEG US regulatory dossiers usable for ARPA submission | CEG | 2026-06-15 | Not Started | 39 | Piano di Caratterizzazione, Analisi di Rischio, Piano di Bonifica equivalents
WS5 | Identify Italian env-law specialist for documentation adaptation | Lapo + Steve | 2026-06-30 | Not Started | 54 | Different from Brenelli (criminal side)
WS6 | Confirm whether CEG insurance extends to Italian projects | Steve | 2026-05-21 | Not Started | 14 | Critical input for our liability gap
WS6 | Get RC professionale quote for env tech intermediary | Lapo | 2026-05-31 | Not Started | 24 | Italian broker; not executing party, only intermediary
WS6 | Commercialista consult: S.r.l. vs holding structure (Italy + Turkey) | Lapo | 2026-05-31 | Not Started | 24 | Liability ring-fencing + intl expansion
WS6 | Investment breakdown + funding allocation (~€100K) | Lapo + Steve | 2026-06-07 | Not Started | 31 | Who funds what
WS6 | Open S.r.l. entity | Lapo | 2026-06-30 | Not Started | 54 | Triggered after structure decision
WS7 | Scoping call with satellite contact (coverage, commercial model) | Lapo | 2026-05-31 | Not Started | 24 | Polluter ID + before/after verification
WS7 | Pull historical CEG project sites for satellite validation case study | CEG | 2026-06-15 | Not Started | 39 | Independent third-party validation asset
WS7 | Brenelli: legal framing for polluter outreach via satellite intel | Lapo | 2026-06-30 | Not Started | 54 | Avoid adversarial trigger
WS8 | Request BioBlend + ISCO technical specs from CEG | Lapo | 2026-06-15 | Not Started | 39 | Subject to IP review
WS8 | CEG: IP/licensing constraints assessment for third-party formulation | CEG | 2026-06-30 | Not Started | 54 | Has CEG done this in other markets?
WS8 | RDC quality + handling capability assessment (ISO 9001/14001/45001) | Lapo | 2026-07-31 | Not Started | 85 | Verify they can hit CEG specs
WS8 | Draft local manufacturing term sheet w/ RDC | Lapo | 2026-08-15 | Not Started | 100 | License / transfer / margin model
WS9 | Hold Istanbul contact warm (no pitch) | Lapo | Ongoing | In Progress | — | DO NOT initiate before WS1 + WS6 closed
WS9 | Draft Istanbul one-pager (regional partner framing) | Lapo | 2026-07-15 | Not Started | 69 | After commercial terms agreed
WS9 | Initial Istanbul call (entity authority) | Lapo | 2026-09-30 | Not Started | 146 | Position as regional tech partner, not CEG-branded
Formulas:
Days to Due = [Due Date]-TODAY()